## Summary-GroupIterationProgress
This report consists of multiple sheets: 1. the group iteration progress summary sheet to be filled at the end of each iteration by the team leader, 2. the project ontribution sheet to be filled by everyone at the end of the semester, 3. the AI Usage Log to be filled by everyone whenever using AI tools 4. the weekly report sheet, one per teamember member, to be filled in each week.
This sheet should be completed by the team leader (or other member in the team) by the end of each iteration.
iteration | Date range | accomplishment summary (such as user stories/tasks completed/big progress, good practices used, etc) | Technical issues summary | non-technical issues summary | Process improvement/plan | # of user story points completed | # of user story points in progress | # of issues opened | # of issues closed | # of issues remained | Total work time (h) | Total Individual work time (h) | Total group meeting time (h) | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | Any other metrics defined in your SPPP
0 | 09/15/2026 – 09/30/2026 | Selected the MBTA Tracker as the project topic, assigned team roles, discussed initial project features and requirements, and started preparing the required project planning documents. | No major technical issues were encountered during this iteration. | Coordinating team members' schedules and assigning responsibilities. | Finalize project requirements and planning documents, improve task coordination, and prepare for the next development iteration. | 0 | 0 | 0 | 0 | 0 | 18 | 12.5 | 5.5 | 1 | 5 | 2 | 1 | 0 | 3.5 | 1 | N/A
1 | 10/01/2026-10/28/2026 | Our team developed the frontend UI and backend API functions for the MBTA Tracker. We implemented API helper functions, created a test page, and tested the project. We also fixed minor code issues, updated the SPPP, reviewed instructor feedback, and assigned the remaining tasks. | We needed more time to understand the MBTA API and process the data. Some API functions and code required adjustments, and additional testing was needed before the demo. | Some team meetings were affected by midterm exams. We also needed better coordination between team members to complete the remaining documentation and project tasks. | We plan to address instructor feedback, complete testing, and fix remaining issues. We will also finish the SPPP, SDD, STD, and Progress Reports, prepare the demo and presentation, and review everything before submission. | 16 | 0 | 10 | 4 | 6 | 84.5 | 67.5 | 17 | 10.5 | 9 | 16.5 | 9 | 9.5 | 22.5 | 7.5 | N/A
2
3

## AIUsageLog
This sheet records all AI usage by your team members
Who | When | Tools | Tasks & Artifact | Final Use (Accepted / Modified / Rejected) | Evaluation/Modification | Link /Appendix/ Prompt history + output summary
Yuexian Feng | 2026-09-27 | ChatGPT | Project documentation and planning | Modified | Reviewed and modified the suggestions based on our MBTA Tracker project and course requirements. | Used ChatGPT to understand the SPPP, Risk Management, and Progress Report requirements and to get guidance on completing the project documentation.
The Anh Tran | 2026-09-27 | ChatGPT | Presentation Draft | Modified | Modified the template and fill in information related to our group work and team members | ChatGPT generated a ready to used template for Iteration 0 Presentation
Wenbo Fan | 2026-09-28 | ChatGPT | Project documentation | Modified | Modified the generated Guideline to fit our project work and team members | Ask Chatgpt to make up a proper guideline for commit and CI/CD plan
Yuchen Bao | 2026-09-27 | ChatGpt | Project Docomentation | Modifeid | Modified SPPP template to set Quality Assurance plan and CI/CD plan for the future development | Use ChatGPT to review the project's basic features and, based on the existing plan, suggest additional features or areas that should be considered for testing.
Zhiao Chu | 2026-09-27 | ChatGpt | Risk Management and Weekly Project Planning | Modified | Reviewed the suggestions and adjusted the risk priorities, task descriptions, and weekly plan based on our actual team discussion and project progress. | Used ChatGPT to review the Risk Management table, check whether the risk values were reasonable, and help organize weekly tasks, team responsibilities, current issues, and plans for the next week.
Yuexian Feng | 2026-10-04 | ChatGPT | Project Requirements and Frontend UI Design | Modified | Reviewed the suggestions and adjusted the frontend UI design based on project requirements. | Used ChatGPT to understand project requirements and explore UI design ideas for the MBTA Green Line B Tracker.
Yuexian Feng | 2026-10-07 | ChatGPT | API Learning and Jira Task Management | Modified | Reviewed the explanations and applied useful suggestions to organize project tasks in Jira. | Used ChatGPT to learn basic API concepts, understand the project code structure, and organize tasks in Jira.
Wenbo Fan | 2026-10-09 | ChatGPT | API basic test page on transform raw data | Modified | Reviewed the B-Test page of API data, and modified it into a more project function targeted page to show the usable data | Used ChatGPT to create a API helper method test page to display the output of API helper function which transform raw JSON data into project usable data
Zhiao Chu | 2026-10-25 | ChatGPT | Demo Setup and Iteration 1 Presentation | Modified | Successfully ran and tested the demo locally. Reviewed and revised the presentation content to match the implemented features and current limitations. | Used ChatGPT to understand the project setup, troubleshoot the demo, summarize implemented features, and draft presentation content.
Zhiao Chu | 2026-10-25 | ChatGPT | Risk Management Review and Validation | Modified | Updated the Week 1 risk management table and manually verified all risks with passed review deadlines. Adjusted the documentation based on the verification results. | Used ChatGPT to help review risk descriptions, organize verification tasks, and improve the wording of risk management documentation.

## projectcontribution
This sheet need to be filled by the end of the semester. You should clearly describe your contribution to the group project in each category in the whole semester.
StudentName | SPPP Document | Requirement Analysis on Pivotaltracker | Design Document (SDD) | Testing Documentation (STD) | Presentation | Implementation (code on Github) | Testing (unittest code on Github or manual testing) | Configuration and Deployment | General communication and management | Other Comments

## Wenbo Fan
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: Backup Project Leader, requirement leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | AI tool log(any AI tools used for what tasks, is it helpful? How do you use the results) | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time for next week
1 | 09/15-09/30 | 3 | 2 | 1 | 1 - research for project idea 2 - design the project 5 - group meeting to plan the project and design the software finishing the documentations |  | 0.5 | 1 |  |  | 0.5 |  |  | Ask Chatgpt to make up a proper guideline for commit and CI/CD plan | 1. finished half of the SPPP 2.Add readme.md to github |  |  | 3-begin implementation | 6
2 | 10/5-10/11 | 6 | 4 | 2 | 1 - analysis the needs and requirement for the project and choose the suitable functions for furture development 2 - create a design page for team to start design the page UI. 3 - building the base frame of the project for team to work on 5 - Team meeting. Commicating on the tech stack we should use on the project. |  | 1 | 2 | 1 |  | 2 |  |  |  | 1.Create Figma project page for UI design 2. Set the tech stack and project plan |  |  | 0 - learning 1 - requirement analysis 2 - design 3 - implementation | 6
3 | 10/12-10/18 | 5 | 5 | 0 | 0 - learning the function and usage of MBTA API 1 - further analysis the needs and requirement for the project and choose the suitable functions for furture development 2 - Decide the functions needs to be finished in iteration 1 3 - Implement API layer helper functions which transform the API raw JSON data to usable data for the project 4 - Create a test page for testing API usage and fetching data into usable data. 5 - Team meeting and split group meeting with Yuchen on API design and API utility functions | 0.5 | 0.5 | 1 | 1 | 1 | 1 |  |  | Used ChatGPT to create a API helper method test page to display the output of API helper function which transform raw JSON data into project usable data | 1. Implemented API usage functions that gets raw JSON data into usable project data 2. create B-Test page which display the transformed data that can be directly used by the project |  |  | 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication | 6
4 | 10/19-10/25 | 5 | 4 | 1 | 1 - Analyze current condition of the project and plan for next week's demo 3 - Further adjust the project implementation and fix minor issues 4 - test the project and make it to be demoable 5 - Group meeting and distribute documentation work to team member for the iteration presentation | 1 |  | 1 | 1 | 1 | 1 |  |  |  | 1. Update the SPPP documentation 2. Clean and Adjust API functions. |  |  | 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication | 6

## Yuexian Feng
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: Backup Project Leader, requirement leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | AI tool log(any AI tools used for what tasks, is it helpful? How do you use the results) | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time for next week
1 | 09/15-10/04 | 3 | 2 | 1 | 0 - review course project requirements and project documents 1 - discuss initial requirements and features for the MBTA Tracker 5 - discuss project ideas with team members, select the project, and assign team roles | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Used ChatGPT to clarify project requirements and documentation. Reviewed and adapted the suggestions for the MBTA Tracker. | 1. Participated in project selection and initial requirements discussion 2. Helped organize and update the Progress Report 3. Reviewed project planning documents and requirements | 1. Some project requirements were unclear. 2. Initial requirements needed further discussion. | 1. Review and clarify the project requirements. 2. Continue discussing requirements with team members. | 1 - continue to refine project requirements 5 - coordinate with team members on project tasks | 4
2 | 10/5-10/11 | 6 | 4 | 2 | 0 - Learned about the project development workflow. 1 - Reviewed project requirements and discussed core features. 2 - Created an initial frontend UI mockup for the Green Line B Tracker. 2 - Discussed basic frontend and backend design. 5 - Attended team meetings on October 7 and 9 to review progress and assign tasks. | 1 | 1 | 2 | 0 | 0 | 2 | 0 | 0 | Used ChatGPT to understand the project workflow, requirements, and basic design. Reviewed and adapted the suggestions for the MBTA Tracker. | 1. Reviewed and clarified project requirements. 2. Discussed core features for the MBTA Tracker. 3. Created an initial frontend UI mockup for the Green Line B Tracker. 4. Participated in frontend and backend design discussions. 5. Helped assign frontend and backend tasks. 6. Supported team planning and task organization. | 1. Some project features needed further clarification. 2. Frontend and backend responsibilities needed discussion. 3. The initial UI design needed further review. | 1. Discussed project requirements during team meetings. 2. Clarified frontend and backend task assignments. 3. Created an initial UI mockup for team review. 4. Plan to improve the design based on team feedback. | 0 - Continue learning about the project structure. 1 - Review and refine project requirements. 2 - Review and improve the frontend UI design. 4 - Plan basic testing for project features. 5 - Follow up on team progress and assigned tasks. | 7
3 | 10/12-10/18 | 5 | 5 | 0 | 0 - Learned basic API concepts and reviewed the GitHub project structure. 1 - Reviewed and organized project requirements. 2 - Worked on the frontend UI design. 4 - Performed basic frontend testing. 5 - Set up Jira and organized project tasks. | 1 | 0.5 | 1.5 | 0 | 0.5 | 1 | 0.5 | 0 | Used ChatGPT to learn basic API concepts, understand the GitHub project structure, and organize tasks in Jira. Reviewed and applied useful suggestions. | 1. Reviewed and improved the frontend UI design. 2. Reviewed the GitHub repository and project code. 3. Organized project requirements. 4. Set up Jira and organized project tasks. 5. Performed basic frontend testing. | 1. The team meeting was canceled due to midterm exams. 2. Team progress was limited during the exam week. 3. Needed more time to understand the backend APIs and project code. | 1. Continued working on individual project tasks. 2. Reviewed the GitHub code and learned basic API concepts. 3. Organized tasks in Jira. 4. Plan to review project progress at the next team meeting. | 0 - Continue learning about backend APIs. 1 - Review and update project requirements. 2 - Improve the frontend UI design. 4 - Continue basic frontend testing. 5 - Meet with team members to review project progress. 5 - Track project tasks and assignments in Jira. | 7
4 | 10/19-10/25 | 5 | 4 | 1 | 1 - Reviewed instructor feedback and project requirements. 4 - Reviewed testing progress and discussed test results with team members. 4 - Worked on software testing and prepared the Software Test Document (STD). 5 - Attended the October 23 team meeting. 5 - Completed meeting minutes, updated the Progress Report, and organized team task assignments. | 0 | 0.5 | 0 | 0 | 1 | 3.5 | 0 | 0 | Used ChatGPT to organize meeting minutes, review project progress, and improve documentation. Reviewed and edited the suggestions before using them. | 1. Reviewed Iteration 1 progress and testing status. 2. Discussed instructor feedback with the team. 3. Attended the October 23 team meeting. 4. Completed Meeting 2 minutes. 5. Organized task assignments for Iteration 1. | 1. Some issues from instructor feedback still need to be addressed. 2. Testing results need to be organized for the STD. 3. Some project documents are not yet complete. | 1. Review and address instructor feedback with the team. 2. Perform manual testing and review automated test results. 3. Complete the STD and update the Progress Report. | 4 - Perform manual testing for the MBTA Tracker. 4 - Run and review automated tests. 4 - Document testing results in the STD. 5 - Update the Progress Report. 5 - Review project deliverables before submission. | 6
5 | 10/26-11/01
6 | 11/02-11/08
7 | 11/09-11/15
8 | 11/16-11/22
9 | 11/23-11/29
10 | 11/30-12/06
11 | 12/07-12/13

## The Anh Tran
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: Backup Project Leader, requirement leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | AI tool log(any AI tools used for what tasks, is it helpful? How do you use the results) | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time for next week
1 | 09/15-09/30 | 3 | 2 | 1 | 1 - define the project requirement and functionality 5 - Initial Team Meeting |  | 2 |  |  |  | 1 |  |  | Use ChatGPT to draft presentation template | Finalized group project idea and prepped for presentation |  |  | Begin Implementation and testing | 6
2 | 10/5-10/11 | 4 | 2 | 2 | 3 - Implemented the first demo/iteration of the MBTA tracker 4 - Test the demo to see if there's any bugs or features misbehaving 5 - Team Meeting, assigning roles and divided work |  |  |  | 1 | 1 | 2 |  |  | Using the Figma design and the laid out requirement to prompt ChatGPT to implement the initial build of the MBTA tracker web app | A demo-able first version of MBTA tracker | There's still a lot of bugs and issues with the API calling and UI | Resolved | Resolve all known bugs and polish out all existing features, ready for first iteration demo | 3
3 | 10/12-10/18 | 5 | 5 | 0 | 1 - Revised and compared our requirement with built demo/iteration 3 - Fixing the bugs from previous development session |  |  | 5 | [5 empty] | Use ChatGPT to determine the issues with API calling and displaying for user's itinerary and correctly displaying the data when the journey direction is reversed | Reversing direction of a given route, e.g. A -> b and B <-A are now functional |  |  | Continue testing the webapp with edge cases to see if there's any bugs left | 2
4 | 10/19-10/25 | 4 | 3 | 1 | 4 - Test the demo to see if there's any bugs or features misbehaving 5 - Team Meeting, wrapping up everything we need for the first demo and Iteration 1 submission |  |  |  |  | 3 | 1 | [6 empty] | Fix any known bugs and continue improving the webapp using Jira's board and our requirement. Add in more lines and branches to the map and search bar to complete full MBTA services | 5

## Yuchen Bao
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: Backup Project Leader, requirement leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | AI tool log(any AI tools used for what tasks, is it helpful? How do you use the results) | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time for next week
1 | 09/15-09/30 | 3 | 2 | 1 | 1 - analyse what language and tools is going to be use in the project 2 - making the quality assurance plan and help with CI/CD plan 5 - having team meeting, be minitue taker and time keeper |  | 1 | 1 | 1 |  |  |  |  | Use ChatGPT to review the project's basic features and, based on the existing plan, suggest additional features or areas that should be considered for testing. | 1. Write MeetinMinutes Documentation for the second meeting. 2. Write half of SPPP Documentation and help verify another half. |  |  | 0 - learn the basic usage of the MBTA API 1 - help define the initial project requirements and see if thers is any feature to be added to project 2 - participate in the initial system design 6 - help to set up the GitHub repository and development environment | 5
2 | 10/01-10/07 | 7 | 5 | 2 | 0 - learning JavaScript Language basics. Learn the knoweledge about popular web developing frameworks. 2 - choose the appropriate computer language, framework to use and choose the CSS tools. 5 - Discuss with my teammates in meeting and discord channel, know each other's tech stacks and contribute to discussion of which tools and frameworks to use to better fit everyone. Help teammates set their Next.js and React Environment on their computer. 6 - Create an empty base project for the project(env setup). Write a short guidance to guide my teammates familiar with set the correct version of Next.js and React up. | 2 | 1 |  |  |  | 2 | 2 |  | Use ChatGpt to help me study the basic syntax of Javascript(especially the part that different from typescript). Use ChatGpt to help me learn the knoweledge of different developing frame works such as: Next.js vs Vite.js, React vs Vue, Styled-component vs Tailwind CSS Use Chatgpt to evluate if my guidance of set the environment is good to use comprehensively. | Create a base enrironment for the project and push it to Github Repo |  |  | 0 - learning 1 - requirement analysis 2 - design 3 - implementation | 8
3 | 10/08 - 10/14 | 8 | 6 | 2 | 0 - learn base knowledge React and Rest API. Learn how to use Jira 1 - analysis the data need to be transfer to the front end. 2 - design the data model in the api layer of our app's server, design the schema and metadata that we might need and give some extra properties and endpoint to make sure the scalability of future development. 3 - implement the API layer files including the communication of our app and the outer open sourced MBTA API, the transistion of the original data and the data model of our own and some some end point that our front end mignt need to use. 5 - attend our group meeting | 1.5 | 1.5 | 1 | 2 |  | 2 |  |  | Use ChatGPT to learn some method and knowledge about React and Rest API Use ChatGPT helps me review the code that I write. | Implement the end point of /predictions, /schedules, /vehicles. Implement api tools(utilities) mbta-api.js for the input data from MBTA API. and push them to Github Repo |  |  | 0 - learning 1 - requirement analysis 2 - design 3 - implementation | 6
4 | 10/15 - 10/21 | 6 | 6 | 0 | 0 - learn how to use Docker.Continue learning JS and React 1 - analysis the features that we might need in next Iteration 2 - check if the previous App's data model is good for more features such as real-time view of MBTA train which we might want. 5 - keep communicate with my teammates | 2 | 2 | 2 |  |  | 0 |  |  | Use ChatGpt to learn some basic docker command and explain me their inner mechanisms. Use ChatGpt to continue learn more about React and JS Use ChatGpt to assist my analysis of the data requirement for the new feature that we might want. | Make some tiny code modification. |  |  | 0 - learning 1 - requirement analysis 2 - design 3 - implementation 5 - communication/management | 6

## Zhiao Chu
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: Backup Project Leader, requirement leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | AI tool log(any AI tools used for what tasks, is it helpful? How do you use the results) | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time for next week
1 | 09/21-09/27 | 6 | 4.5 | 1.5 | 1 - review project requirements and discuss project scope and responsibilities 5 - attend team meetings, coordinate team members, confirm task assignments and deadlines, and discuss project risks 6 - manage Git branches and repository, check team submissions and merge completed work into main branch 7 - organize project notes and contribute to the risk management table |  | 0.5 |  |  |  | 2 | 1 | 1 | Used ChatGPT to help organize the risk management table, review Git workflow, and improve the wording of project documentation. | 1. Coordinated team responsibilities and weekly task assignments. 2. Managed the Git repository and merged completed team work into the main branch. 3. Contributed to the project risk management table and project documentation. 4. Participated in team meetings to confirm project scope, tasks, and deadlines. | 1. Team members had different schedules, making coordination more difficult. 2. Some risk estimates required additional discussion to make them realistic. | 1. Clarified responsibilities during the team meeting and confirmed task assignments with team members. 2. Continue to track progress and update the risk table when new issues appear. | 1 - continue requirement analysis and refine project requirements 2 - discuss the project design and workflow with the team 5 - track team progress, organize meetings, and adjust task assignments if necessary | 6
2 | 10/05-10/11 | 6 | 4 | 2 | 0 - Learned the project workflow and reviewed the GitHub repository structure. 1 - Reviewed the MBTA Tracker requirements and project scope. 5 - Discussed project progress and upcoming tasks with team members. 6 - Installed Docker Desktop and verified the Docker and Docker Compose environment on Windows. | 1 | 0.5 | 1 | 1 |  | 0.5 | 2 |  | Used ChatGPT to understand the GitHub workflow, Docker installation requirements, and basic project setup. Reviewed the suggestions and verified the local environment manually. | 1. Reviewed the project requirements and repository structure. 2. Set up and verified the local Docker environment. 3. Participated in discussions about project progress and upcoming tasks. | 1. Needed time to become familiar with the project structure. 2. Docker setup and configuration required additional learning. | 1. Reviewed the repository and project documentation. 2. Successfully installed and verified Docker and Docker Compose. 3. Plan to practice container operations and continue reviewing project requirements. | 0 - Continue learning Docker container operations. 1 - Review repository assignment requirements. 4 - Practice basic container testing. 5 - Prepare repository documentation. 6 - Continue the Docker lab setup. | 5
3 | 10/12-10/18 | 6 | 5 | 1 | 0 - Learned Docker container operations and reviewed project setup instructions. 1 - Reviewed the GitHub repository requirements and project documentation. 4 - Checked the local Docker environment and practiced basic container operations. 5 - Prepared repository assignment documentation and organized supporting evidence. 6 - Worked on the Docker lab setup and explored container management commands. | 0.5 | 0.5 |  | 1 | 1 | 1.5 | 1.5 |  | Used ChatGPT to understand Docker commands, review repository assignment requirements, and organize technical documentation. Checked the suggested commands and adjusted the documentation based on the actual environment. | 1. Reviewed the GitHub repository and assignment requirements. 2. Worked on the Docker lab and practiced container management operations. 3. Prepared repository documentation and supporting evidence. 4. Continued reviewing the project environment and setup procedures. | 1. The team meeting was canceled due to midterm exams. 2. Limited time was available for project work during the exam week. 3. Some Docker operations required additional practice. | 1. Continued individual project tasks during the exam week. 2. Reviewed Docker commands and the repository documentation. 3. Plan to resume team coordination and test the current application demo. | 4 - Run and test the MBTA Tracker demo locally. 5 - Prepare the Iteration 1 presentation. 5 - Update the risk management table and verify past-due risks. 6 - Configure the application environment and install required dependencies. | 6
4 | 10/19-10/25 | 6.5 | 5.5 | 1 | 4 - Test the local demo, including station selection, route visualization, and departure information display. 5 - Prepare the Iteration 1 presentation, update the Week 1 risk management table, and verify all risks with passed review deadlines. 6 - Configure the local environment, install dependencies, and successfully launch the MBTA Tracker demo. |  |  |  | 1 | 1 | 3 | 1.5 |  | Used ChatGPT to review demo setup instructions, organize the Iteration 1 presentation content, and improve the wording of project documentation. Demo functionality and risk statuses were verified manually. | 1. Successfully launched the MBTA Tracker demo and performed basic functional checks. 2. Prepared the Iteration 1 presentation covering implemented features, architecture, testing, and future plans. 3. Updated the Week 1 risk management table and verified all risk items with passed review deadlines. | 1. Live departure predictions were unavailable during the late-night demo. 2. Clicking stations on the map can cause confusion between starting point and destination selection. | 1. Retest live predictions during normal service hours. 2. Recommend clearer starting/destination selection controls for the next iteration. 3. Continue monitoring the verified risks and updating their statuses as needed. | 4 - Perform additional functional testing during normal service hours. 5 - Finalize the Iteration 1 presentation and prepare the live demonstration. 5 - Continue tracking project risks and documenting outstanding issues. | 6