## Summary-GroupIterationProgress
This report consists of multiple sheets: 1. the group iteration progress summary sheet to be filled at the end of each iteration by the team leader, 2. the project ontribution sheet to be filled by everyone at the end of the semester, 3. the AI Usage Log to be filled by everyone whenever using AI tools 4. the weekly report sheet, one per teamember member, to be filled in each week.
This sheet should be completed by the team leader (or other member in the team) by the end of each iteration.
iteration | Date range | accomplishment summary (such as user stories/tasks completed/big progress, good practices used, etc) | Technical issues summary | non-technical issues summary | Process improvement/plan | # of user story points completed | # of user story points in progress | # of issues opened | # of issues closed | # of issues remained | Total work time (h) | Total Individual work time (h) | Total group meeting time (h) | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | Any other metrics defined in your SPPP
0 | 09/15/2026 – 09/30/2026 | Selected the MBTA Tracker as the project topic, assigned team roles, discussed initial project features and requirements, and started preparing the required project planning documents. | No major technical issues were encountered during this iteration. | Coordinating team members' schedules and assigning responsibilities. | Finalize project requirements and planning documents, improve task coordination, and prepare for the next development iteration. | 0 | 0 | 0 | 0 | 0 | 18 | 12.5 | 5.5 | 1 | 5 | 2 | 1 | 0 | 3.5 | 1 | N/A
1
2
3

## AIUsageLog
This sheet records all AI usage by your team members
Who | When | Tools | Tasks & Artifact | Final Use (Accepted / Modified / Rejected) | Evaluation/Modification | Link /Appendix/ Prompt history + output summary
Yuexian Feng | 2026-09-27 | ChatGPT | Project documentation and planning | Modified | Reviewed and modified the suggestions based on our MBTA Tracker project and course requirements. | Used ChatGPT to understand the SPPP, Risk Management, and Progress Report requirements and to get guidance on completing the project documentation.
The Anh Tran | 2026-09-27 | ChatGPT | Presentation Draft | Modified | Modified the template and fill in information related to our group work and team members | ChatGPT generated a ready to used template for Iteration 0 Presentation
Wenbo Fan | 2026-09-28 | ChatGPT | Project documentation | Modified | Modified the generated Guideline to fit our project work and team members | Ask Chatgpt to make up a proper guideline for commit and CI/CD plan
Yuchen Bao | 2026-09-27 | ChatGpt | Project Docomentation | Modifeid | Modified SPPP template to set Quality Assurance plan and CI/CD plan for the future development | Use ChatGPT to review the project's basic features and, based on the existing plan, suggest additional features or areas that should be considered for testing.
Zhiao Chu | 2026-09-27 | ChatGpt | Risk Management and Weekly Project Planning | Modified | Reviewed the suggestions and adjusted the risk priorities, task descriptions, and weekly plan based on our actual team discussion and project progress. | Used ChatGPT to review the Risk Management table, check whether the risk values were reasonable, and help organize weekly tasks, team responsibilities, current issues, and plans for the next week.

## projectcontribution
This sheet need to be filled by the end of the semester. You should clearly describe your contribution to the group project in each category in the whole semester.
StudentName | SPPP Document | Requirement Analysis on Pivotaltracker | Design Document (SDD) | Testing Documentation (STD) | Presentation | Implementation (code on Github) | Testing (unittest code on Github or manual testing) | Configuration and Deployment | General communication and management | Other Comments

## Yuexian Feng
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: Backup Project Leader, requirement leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | AI tool log(any AI tools used for what tasks, is it helpful? How do you use the results) | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time for next week
1 | 05/10-05/16 | 7 | 6 | 1 | 0 - learn git and django, read several tutorials 1 - define high level requirements, 5 - make project plan, send reminders to team members 6 - set up git 7 - research similar products, prepare presentation | 3 | 1 |  |  |  | 0.5 | 1 | 0.5 | Use chatgpt to research Django, and elicitate some high level requirements, which we discussed in the team meeting, Use copilot to generate an initial code sketlon, though it requires some manual modification to get it running | 1. Write 3 sections of SPPP 2. Set up git, commit a test message on git 3. Participate in Iteration 0 presentation | 1. not familar with Django framework, hard to write any code on it 2. communication is not clear. Task assignments is not clear. | 1. finish Django tutorial in 2 weeks, be able to create simple Djano hello world project next week 2. Send task assignments to all members again | 0 - continue to learn Django 1 - continue to define requirements 3 - implement a basic hello world on Django | 6
1 | 09/15-09/30 | 3 | 2 | 1 | 0 - review course project requirements and project documents 1 - discuss initial requirements and features for the MBTA Tracker 5 - discuss project ideas with team members, select the project, and assign team roles | 1 | 1 |  |  |  | 1 |  |  | Used ChatGPT to clarify project requirements and documentation. Reviewed and adapted the suggestions for the MBTA Tracker. | 1. Participated in project selection and initial requirements discussion 2. Helped organize and update the Progress Report 3. Reviewed project planning documents and requirements | 1. Some project requirements were unclear. 2. Initial requirements needed further discussion. | 1. Review and clarify the project requirements. 2. Continue discussing requirements with team members. | 1 - continue to refine project requirements 5 - coordinate with team members on project tasks | 4

## Wenbo Fan
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: Backup Project Leader, requirement leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | AI tool log(any AI tools used for what tasks, is it helpful? How do you use the results) | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time for next week
1 | 05/10-05/16 | 7 | 6 | 1 | 0 - learn git and django, read several tutorials 1 - define high level requirements, 5 - make project plan, send reminders to team members 6 - set up git 7 - research similar products, prepare presentation | 3 | 1 |  |  |  | 0.5 | 1 | 0.5 | Use chatgpt to research Django, and elicitate some high level requirements, which we discussed in the team meeting, Use copilot to generate an initial code sketlon, though it requires some manual modification to get it running | 1. Write 3 sections of SPPP 2. Set up git, commit a test message on git 3. Participate in Iteration 0 presentation | 1. not familar with Django framework, hard to write any code on it 2. communication is not clear. Task assignments is not clear. | 1. finish Django tutorial in 2 weeks, be able to create simple Djano hello world project next week 2. Send task assignments to all members again | 0 - continue to learn Django 1 - continue to define requirements 3 - implement a basic hello world on Django | 6
1 | 09/15-09/30 | 3 | 2 | 1 | 1 - research for project idea 2 - design the project 5 - group meeting to plan the project and design the software finishing the documentations |  | 0.5 | 1 |  |  | 0.5 |  |  | Ask Chatgpt to make up a proper guideline for commit and CI/CD plan | 1. finished half of the SPPP 2.Add readme.md to github |  |  | 3-begin implementation | 6

## The Anh Tran
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: Backup Project Leader, requirement leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | AI tool log(any AI tools used for what tasks, is it helpful? How do you use the results) | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time for next week
1 | 05/10-05/16 | 7 | 6 | 1 | 0 - learn git and django, read several tutorials 1 - define high level requirements, 5 - make project plan, send reminders to team members 6 - set up git 7 - research similar products, prepare presentation | 3 | 1 |  |  |  | 0.5 | 1 | 0.5 | Use chatgpt to research Django, and elicitate some high level requirements, which we discussed in the team meeting, Use copilot to generate an initial code sketlon, though it requires some manual modification to get it running | 1. Write 3 sections of SPPP 2. Set up git, commit a test message on git 3. Participate in Iteration 0 presentation | 1. not familar with Django framework, hard to write any code on it 2. communication is not clear. Task assignments is not clear. | 1. finish Django tutorial in 2 weeks, be able to create simple Djano hello world project next week 2. Send task assignments to all members again | 0 - continue to learn Django 1 - continue to define requirements 3 - implement a basic hello world on Django | 6
1 | 09/15-09/30 | 3 | 2 | 1 | 1 - define the project requirement and functionality |  | 2 | [6 empty] | Use ChatGPT to draft presentation template | Finalized group project idea and prepped for presentation |  |  | Begin Implementation and testing | 6

## Zhiao Chu
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: Backup Project Leader, requirement leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | AI tool log(any AI tools used for what tasks, is it helpful? How do you use the results) | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time for next week
1 | 05/10-05/16 | 7 | 6 | 1 | 0 - learn git and django, read several tutorials 1 - define high level requirements, 5 - make project plan, send reminders to team members 6 - set up git 7 - research similar products, prepare presentation | 3 | 1 |  |  |  | 0.5 | 1 | 0.5 | Use chatgpt to research Django, and elicitate some high level requirements, which we discussed in the team meeting, Use copilot to generate an initial code sketlon, though it requires some manual modification to get it running | 1. Write 3 sections of SPPP 2. Set up git, commit a test message on git 3. Participate in Iteration 0 presentation | 1. not familar with Django framework, hard to write any code on it 2. communication is not clear. Task assignments is not clear. | 1. finish Django tutorial in 2 weeks, be able to create simple Djano hello world project next week 2. Send task assignments to all members again | 0 - continue to learn Django 1 - continue to define requirements 3 - implement a basic hello world on Django | 6
1 | 09/21-09/27 | 6 | 4.5 | 1.5 | 1 - review project requirements and discuss project scope and responsibilities 5 - attend team meetings, coordinate team members, confirm task assignments and deadlines, and discuss project risks 6 - manage Git branches and repository, check team submissions and merge completed work into main branch 7 - organize project notes and contribute to the risk management table |  | 0.5 |  |  |  | 2 | 1 | 1 | Used ChatGPT to help organize the risk management table, review Git workflow, and improve the wording of project documentation. | 1. Coordinated team responsibilities and weekly task assignments. 2. Managed the Git repository and merged completed team work into the main branch. 3. Contributed to the project risk management table and project documentation. 4. Participated in team meetings to confirm project scope, tasks, and deadlines. | 1. Team members had different schedules, making coordination more difficult. 2. Some risk estimates required additional discussion to make them realistic. | 1. Clarified responsibilities during the team meeting and confirmed task assignments with team members. 2. Continue to track progress and update the risk table when new issues appear. | 1 - continue requirement analysis and refine project requirements 2 - discuss the project design and workflow with the team 5 - track team progress, organize meetings, and adjust task assignments if necessary | 6

## Yuchen Bao
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: Backup Project Leader, requirement leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | AI tool log(any AI tools used for what tasks, is it helpful? How do you use the results) | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time for next week
1 | 05/10-05/16 | 7 | 6 | 1 | 0 - learn git and django, read several tutorials 1 - define high level requirements, 5 - make project plan, send reminders to team members 6 - set up git 7 - research similar products, prepare presentation | 3 | 1 |  |  |  | 0.5 | 1 | 0.5 | Use chatgpt to research Django, and elicitate some high level requirements, which we discussed in the team meeting, Use copilot to generate an initial code sketlon, though it requires some manual modification to get it running | 1. Write 3 sections of SPPP 2. Set up git, commit a test message on git 3. Participate in Iteration 0 presentation | 1. not familar with Django framework, hard to write any code on it 2. communication is not clear. Task assignments is not clear. | 1. finish Django tutorial in 2 weeks, be able to create simple Djano hello world project next week 2. Send task assignments to all members again | 0 - continue to learn Django 1 - continue to define requirements 3 - implement a basic hello world on Django | 6
1 | 09/15-09/30 | 3 | 2 | 1 | 1 - analyse what language and tools is going to be use in the project 2 - making the quality assurance plan and help with CI/CD plan 5 - having team meeting, be minitue taker and time keeper |  | 1 | 1 | 1 |  |  |  |  | Use ChatGPT to review the project's basic features and, based on the existing plan, suggest additional features or areas that should be considered for testing. | 1. Write MeetinMinutes Documentation for the second meeting. 2. Write half of SPPP Documentation and help verify another half. |  |  | 0 - learn the basic usage of the MBTA API 1 - help define the initial project requirements and see if thers is any feature to be added to project 2 - participate in the initial system design 6 - help to set up the GitHub repository and development environment | 5