## Sheet1
This sheet provides some common risks in student projects. You should check if it applies to your group project. You should also feel free to add other risks. Exemplary analysis is also added.
Risk Category | Risk Title | Description | Estimated likelihood of occurrence (L: 1-5 with 1 lowest likelihood) | Estimated Impact (I:1-5 with 1 lowest impact) | Estimated retirement Cost (C: 1-5 with 1 lowest cost) | Priority (lowest number has high priority) (6-L)*(6-I)*C) | Responsible engineer | Target completion date | Detailed plan | Execution summary | Status
personel | Loss team members | One or more team members drop the class | 2 | 4 | 4 | 4*2*4=32 | team leader and all members | 2026-12-21 | Redefine the project scope if necessary, and assign the tasks to other team members. | No one dropped the class so far | Open
add new team members
| Lack of motivation or responsibility | A team member may delay or fail to complete assigned work, which could affect the progress of the whole team. | 3 | 3 | 3 | 3*3*3=27 | Team Leader and all developers | 2026-12-21 | Assign clear tasks and deadlines in advance. Reassign tasks when necessary. | No issues have been identified so far. | Open
Communication | duplicate work | Two or more members may work on the same task without realizing it, wasting development time. | 2 | 2 | 3 | 4*4*3=48 | Team Leader and all members | 2026-12-21 | Keep the team updated about current work and completed tasks weekly. | No issues have been identified so far. | Open
worked on wrong components
useless work
inconsistent work
Requirements | unclear requirements | Team members may understand features such as route selection, arrivals, alerts, or refresh behavior differently, causing rework. | 3 | 3 | 1 | 3*3*1=9 | Requirement Leader and Design and Implementation Leader | 2026-10-26 | Before implementation, the team should communicate proactively and distill respective understandings of each concept. | No issues have been identified so far. | Open
| scope creep | Adding too many optional features may take time away from the essential MBTA tracker functions. | 2 | 3 | 2 | 4*3*2=24 | Team Leader and Requirement Leader | 2026-11-16 | Prioritize requirements before implementation and make sure high-priority features are completed first. | No issues have been identified so far. | Open
constant requirements changes
Management | improper task assignments | Tasks may be assigned to members without considering their roles, experience, or current workload. | 2 | 3 | 2 | 4*3*2=24 | Team Leader and all members | 2026-10-26 | Assign tasks based on team roles and experience. Encourage team members to help each other when someone is unfamiliar with a specific task. | No issues have been identified so far. | Open
improper planning
lack of management skills
Technology competence | Not familiar with the framework used | Some team members may be unfamiliar with the selected web framework, which could slow development or cause implementation mistakes. | 3 | 4 | 3 | 3*2*3=18 | Design and Implementation Leader and all members | 2026-11-16 | Confirm the framework early and provide basic setup instructions. | No issues have been identified so far. | Open
| Not familiar with the programming language used | Some team members may have limited experience with the programming languages selected for the project, which could reduce development efficiency. | 1 | 4 | 1 | 5*2*1=10 | Design and Implementation Leader and all members | 2026-09-28 | Use commonly understood languages when possible and share examples or references for project-specific coding patterns. | The team has agreed on the main programming languages to be used. | Open
| Not familiar with unit testing | Team members may not be familiar with writing effective unit tests, which could result in insufficient test coverage or defects being discovered late. | 3 | 3 | 2 | 3*3*2=18 | QA Leader and all developers | 2026-11-16 | Define basic unit-testing expectations and provide simple examples for the project. | No issues have been identified so far. | Open
Other technology incompetence
Not familiar with Git
Design and implementation | Improper design | Poor separation between the user interface, application logic, and MBTA API access could make the system harder to test and modify. | 3 | 4 | 2 | 3*2*2=12 | Design and Implementation Leader | 2026-10-26 | Review the application structure before major implementation and keep API access, data processing, and user-interface logic reasonably separated. | The team needs to start preparing for the modularized design right now. | Open
improper technology stack
Messy code
Testing | Not enough testing | Important cases such as missing predictions, API failures, or incorrect route and stop selection may not be discovered before integration or demo. | 3 | 4 | 3 | 3*2*3=18 | QA Leader and all developers | 2026-12-21 | Each developer should test the features they implement. The QA Leader will coordinate integration and failure-case testing before the final release. | No issues have been identified so far. | Open
Integration and deployment | Not enough time for integration and deployment | Features may work separately but fail when combined if integration is delayed until the end of the project. | 3 | 4 | 3 | 3*2*3=18 | Configuration Leader and Design and Implementation Leader | 2026-12-21 | Follow an iterative workflow: complete partial functionality, integrate and publish a demo, add new features, and integrate again. | No issues have been identified so far. | Open
External Service (extra) | MBTA API unavailable | The application depends on the MBTA API, so temporary API or network failures may prevent arrival and alert information from loading. | 2 | 3 | 4 | 4*3*4=48 | Design and Implementation Leader and QA Leader | 2026-12-21 | Handle failed requests clearly, provide retry behavior, and use sample or mocked responses during development and testing | No issues have been identified so far. | Open
The team member who is adding the new feature should be the one who determines what is correct for the new functionality that was added.
Work together as a team to make sure each developer has the same environment. This is useful so that there aren't accidental bugs added due to environment issues.